## Risks
Risk Assessment Document - Property Tycoon Software Engineering Project | [9 empty] | Risk Levels: | None | Very Low | Low | Medium | High | Very High | Extreme
Members: | Kristian | Karen | Sean | Pim | Zach |  |  |  |  | Probabillity Levels: | Low | Moderate | High
Risk Number |  |  |  | Strategy |  | Type | Probability | Effects | Level | Effects Levels: | Moderate | Serious | Catastrophic
| Risk | Identification | Analysis | Planning | Monitoring
1 | Member absence. | Reduction in productivity and delay in team input. Communication disruption. | Weather has caused a reduction in team members present during team meetings. Frequent meetings of 2 or 3 members rather than all members. | Keep team contact to confirm attendance and plan journeys to avoid absence. | Take regular attendance and check weather. | People | High | Serious | High
2 | Client updates requirements: Ability to trade properties. | The software may not satisfy mandatory non-functional requirements. | The client decides to update the requirements to include trading. | Actively query client for answers and details. | Check Questions and Answers and client updates regularly. | Requirements | Moderate | Serious | High
3 | Client updates requirements: Replacing players with game agents if they retire early. | The software may not satisfy desirable non-functional requirements. | The client decides to update the requirements to include player replacement. | Actively query client for answers and details. | Check Questions and Answers and client updates regularly. | Requirements | Moderate | Serious | Low
4 | Project Manager ill. | Disruption to integral team management. | The Project Manager is unable to attend team meetings. Team is without aim or direction momentarily. | Assign possible backup or vice project manager | Take regular attendance. | Organisational | Low | Catastrophic | High
5 | Underestimating time taken to complete tasks in project plan. | Project Plan task takes longer than expected. | Some stages have a high risk of taking longer to complete. Particularly the main coding stages including GUI implementation and Software Model implementation. | Assign more members to a task appropriately, adjust deadlines or reduce workload for task. | Regularly assess progress of task by asking team members about their task. | Estimation | High | Catastrophic | Very High
6 | Code doesn't function properly. | Code libraries and packages fail to function or integrate. | Members fail to communicate effectively leading to a break down in the project code integrity. | Research essential code libraries and packages beforehand and maintain communcation between coding members. | Test code regularly. | Tools | High | Serious | High
7 | Code doesn’t function properly. | Improper code whereby code doesn't employ correct functionality. | Member experience is insufficient for task. Code functions incorrectly leading to poor software and capability. | Revise coding experience and practice programming beforehand. | Test code regularly. | Organisational | Moderate | Serious | Medium
8 | Software doesn't function properly. | Software does not function as desired. | Faults in code cause direct impact on software capability or displays design flaws. | Revise design. | Assess design and result consistently. | Organisational | Moderate | Serious | Medium
9 | Members do not possess required experience or skills. | Lack of skills or members assigned to tasks incorrectly. | Incorrect asssignment or lack of skills causes undesirable or low quality project output and software. | Assess available skillset beforehand and ensure correct task assignment. Recruit new or additional members with required skills. | Briefly interview members prior to task assigment to determine most appropriate task assigment and their skills. | People | Low | Moderate | Very Low
10 | The size of the entire project is underestimated. | The project workload is underestimated. | The anticipated workload for the project is underestimated and therefore members are overworked or do not produce high quality results, software and code. | Keep in mind the overall workload for the project. Implement an effective Project Plan for this purpose | Prior to each task, assess the anticipated workload for the task and plan accordingly. | Estimation | Moderate | Serious | Medium

## Changes and Updates
Changes and Updates
Number | Date | Change description
1 | 2018-03-02 | Created document
2 | 2018-03-02 | Added member absence risk.
3 | 2018-03-02 | Added trading risk.
4 | 2018-03-02 | Added replacing players risk.
5 | 2018-03-02 | Added project manager ill risk.
6 | 2018-03-02 | Added task overestimation risk.
7 | 2018-03-02 | Added code functionality risk.
8 | 2018-03-02 | Added code functionality risk.
9 | 2018-03-02 | Added software functionality risk.
10 | 2018-03-02 | Added skills risk.
11 | 2018-03-02 | Added project size risk.